## Links and References
ChatGPT | <- Context and About the App

## Plan
Lifecycle
Project Setup
Backend Infrastructure |  | Onboarding
Design System & Theme |  | Discovery
Navigation Structure |  | Profile Detail
Screen Implementation |  | Match Animation
State Management |  | Chat Interface
Testing |  | Settings/Preferences
Documentation
Tools
Android Studio | IDE
Pixel 8 (Stable) | Emulator
App Manager | Studio
Languages | Java, React Native, Node

## initial sign-up formalities
User data
Name | First Name | Lastname
Phone Number | OTP | Verification
Geo Location | GPS | Always ON
Gender | M/F/Pro+MAX+ULTRA
Religion
Languages Prefered
Age | Above to 21+
Make Profile visible to all | Yes or No
User Name
Hobbies | Likes | Travel | Music | Dance | Party
Introvert | Extrovert | Ambivert | ProVert
Kinks | Dating | LongTerm | ShortTerm | ONS | Friend | Fun | Socialize | Mixers | Wine Tasting | Movie | Group Events
Languages
Login Email | Only GMAIL, MICROSOFT, Phone, YAHOO | Prevent Temp Mail and Temp Number |  |  | 2 way verification

## Entity Arch
Basic Prototype | Pure App User Arch
REGISTERED | ANONYMOUS_JOIN
↓ | ↓
VERIFIED (Phone + Photos) | INTENT_POSTED (expires in 24h)
↓ | ↓
ACTIVE | CHAT_ACTIVE (1:1 only)
↓ | ↓
MATCHED | CONNECTION_EXPIRED
↓ | ↓
ENGAGED (Meaningful chat) | USER_GHOSTED (soft reset)
↓
PAUSED / INACTIVE / BANNED
| Aspect | PURE | Traditional Dating Apps
9. Chat Architecture (User Behavior Shaping) | Identity | Anonymous | Persistent
Chat Rules | Profiles | None | Mandatory
1:1 only | Matches | Temporary | Permanent
No screenshots (detected heuristically) | Chat | Time-limited | Unlimited
No forwarding | User Value | Presence | Popularity
Auto-expire | Abuse Control | Rate + Visibility | Moderation-heavy
Media locked behind trust

## Tech Stack
Purpose | Tech | Data | Storage
User & Profile | PostgreSQL
Chat Messages | Cassandra / DynamoDB | Intents | PostgreSQL + TTL
Media Metadata | PostgreSQL | Chat Sessions | Redis / DynamoDB
Search & Discovery | Elasticsearch | Reputation | Internal Scoring DB
Cache | Redis | Abuse Signals | Event Store
Events | Kafka / PubSub
Class Diagram
Matching Engine (India-Optimized)
Hybrid Model
Rule-Based (Hard Filters)
Age range
Location
Intent
Language
ML-Based (Soft Ranking)
Conversation success
Profile engagement
Similar value clusters
Reputation score

## Dating App Task Plan
Phase | Task ID | Task Name | Status | Priority | Owner | Start Date | End Date | Notes
Information Gathering | 1 | Identify target audience segments in India | Complete |  |  |  |  | >21yrs | Market and User analysis based on current economy
Information Gathering | 2 | Study top dating apps in India (Tinder, Bumble, Hinge, Aisle) | Complete
Information Gathering | 3 | Analyze unique features and gaps in existing Indian dating apps | Complete
Information Gathering | 4 | Define core problem the app will solve | Complete
Information Gathering | 5 | Decide app positioning (premium, freemium, women-first, serious dating) | Complete |  |  |  |  | Let in Written
Information Gathering | 6 | Research Indian cultural and safety considerations | Complete |  |  |  |  | Let in Written
Information Gathering | 7 | Define primary user personas | Complete
Information Gathering | 8 | Define core features | Complete
Information Gathering | 9 | Define advanced features | Complete
Information Gathering | 10 | Decide onboarding flow and user journey | Complete |  |  |  |  | Left to be made fare
Information Gathering | 11 | Decide matching algorithm logic | Complete
Information Gathering | 12 | Research legal requirements in India | Complete | [5 empty] | https://docs.google.com/document/d/1mB6xphpBzBzxYEOwIGlgllySxcH0XlNcHJfq8F3gOFM/edit?usp=sharing
Information Gathering | 13 | Research content moderation requirements | Complete | [5 empty] | Pending items market analysis
Information Gathering | 14 | Research safety and reporting mechanisms | Complete
Information Gathering | 15 | Decide platform strategy | Complete
Information Gathering | 16 | Decide monetization strategy | Complete
Information Gathering | 17 | Define MVP feature list | Complete
Information Gathering | 18 | Define future feature roadmap | Complete
Information Gathering | 19 | Prepare high-level app architecture plan | Complete
Information Gathering | 20 | Finalize tech stack | Complete
Information Gathering | 21 | Estimate development timeline | Complete
Information Gathering | 22 | Estimate infrastructure and operational costs | Complete
Development - Design | 23 | Create low-fidelity wireframes
Development - Design | 24 | Create high-fidelity UI designs
Development - Design | 25 | Design onboarding and profile creation screens
Development - Design | 26 | Design match discovery and swipe screens
Development - Design | 27 | Design chat and messaging UI
Development - Design | 28 | Design subscription and payment UI
Development - Design | 29 | Design safety, block and report screens
Development - Design | 30 | Create clickable prototype (Figma)
Development - Design | 31 | Review and finalize UI/UX
Development - Backend | 32 | Set up backend project structure
Development - Backend | 33 | Set up database schema
Development - Backend | 34 | Implement user authentication
Development - Backend | 35 | Implement profile creation and editing APIs
Development - Backend | 36 | Implement image upload and optimization
Development - Backend | 37 | Implement location-based matching logic
Development - Backend | 38 | Implement swipe and match logic
Development - Backend | 39 | Implement real-time chat system
Development - Backend | 40 | Implement message storage and retrieval
Development - Backend | 41 | Implement user block and report system
Development - Backend | 42 | Implement content moderation checks
Development - Backend | 43 | Implement notification system
Development - Backend | 44 | Implement subscription and purchase logic
Development - Backend | 45 | Implement admin panel APIs
Development - Backend | 46 | Implement analytics and event tracking
Development - Frontend | 47 | Set up mobile app project
Development - Frontend | 48 | Implement authentication screens
Development - Frontend | 49 | Implement onboarding flow
Development - Frontend | 50 | Implement profile creation UI
Development - Frontend | 51 | Implement swipe and match UI
Development - Frontend | 52 | Implement chat UI
Development - Frontend | 53 | Implement notifications UI
Development - Frontend | 54 | Implement subscription purchase flow
Development - Frontend | 55 | Implement settings and account management
Development - Frontend | 56 | Implement safety and reporting UI
Development - Frontend | 57 | Integrate backend APIs
Development - Frontend | 58 | Handle error states and edge cases
Testing | 59 | Perform backend unit testing
Testing | 60 | Perform frontend component testing
Testing | 61 | Perform integration testing
Testing | 62 | Test real-time chat performance
Testing | 63 | Test location-based matching accuracy
Testing | 64 | Test payment and subscription flows
Testing | 65 | Test security and data privacy
Testing | 66 | Perform load testing
Testing | 67 | Fix bugs and performance issues
Testing | 68 | Conduct internal beta testing
Testing | 69 | Conduct closed user testing
Testing | 70 | Gather user feedback
Testing | 71 | Improve UX based on feedback
Release Preparation | 72 | Optimize app performance
Release Preparation | 73 | Optimize backend scaling and caching
Release Preparation | 74 | Prepare production environment
Release Preparation | 75 | Configure monitoring and logging
Release Preparation | 76 | Finalize admin moderation workflows
Release Preparation | 77 | Prepare privacy policy and terms of service
Release Preparation | 78 | Prepare app store screenshots and descriptions
Monetization & Launch | 79 | Create Google Play Developer account
Monetization & Launch | 80 | Prepare app signing and keystore
Monetization & Launch | 81 | Configure app package and versioning
Monetization & Launch | 82 | Upload app to Google Play Console
Monetization & Launch | 83 | Configure app content rating
Monetization & Launch | 84 | Configure data safety section
Monetization & Launch | 85 | Add privacy policy URL
Monetization & Launch | 86 | Submit app for Google Play review
Monetization & Launch | 87 | Configure Google Play Billing
Monetization & Launch | 88 | Create subscription plans
Monetization & Launch | 89 | Create one-time purchase products
Monetization & Launch | 90 | Implement pricing experiments
Monetization & Launch | 91 | Test billing flows in production
Monetization & Launch | 92 | Track conversion metrics
Monetization & Launch | 93 | Optimize pricing based on user behavior
Monetization & Launch | 94 | Set up Firebase Analytics
Monetization & Launch | 95 | Set up Google Analytics events
Monetization & Launch | 96 | Set up Firebase Crashlytics
Monetization & Launch | 97 | Set up Google Ads account
Monetization & Launch | 98 | Create app install ad campaigns
Monetization & Launch | 99 | Create retargeting campaigns
Monetization & Launch | 100 | Optimize Play Store listing (ASO)
Monetization & Launch | 101 | Track CPI and LTV metrics
Monetization & Launch | 102 | Improve onboarding conversion rates
Monetization & Launch | 103 | Optimize matching and engagement metrics
Monetization & Launch | 104 | Monitor app reviews and ratings
Monetization & Launch | 105 | Respond to user reviews
Monetization & Launch | 106 | Improve safety and moderation tools
Monetization & Launch | 107 | Release regular feature updates
Monetization & Launch | 108 | Run A/B tests for features
Monetization & Launch | 109 | Optimize server costs
Monetization & Launch | 110 | Scale infrastructure as users grow

## Functionalities
Messaging
Video Call
Friend Request
Status
Reels
UI upgrade
Music profile
Custom UI
Location based hot spots

## Future Ideas
Name | Idea
Viral | Lets make the Animated UI and provide according to the plan they purchase and provide a customizeable UI plan also
We can ask the user for the time period they want to be in contact through the app

## API
GraphQL for API's
auth | Third Party Auth
Post API - User Info
Get API - User Info
Put API - User Info
Delete API - Account Deletion

## APP Design Link
Authentication | User Profile | Dashboard
https://dribbble.com/shots/23148185-AuthKit-com |  | https://dribbble.com/shots/24990264-Dating-Mobile-iOS-App-Design-Concept
finpal: AI Finance Assistant App - Sign In/Sign Up Auth UIUX by finterface on Dribbble |  | https://www.figma.com/community/file/1373477512227156451/online-dating-app-dashboard
https://dribbble.com/shots/16452525-2FAST-Authenticator-App-Login-With-Passcode |  | https://dribbble.com/shots/23284082-Dating-Log-App
https://mobbin.com/search/apps/ios?content_type=screens&q=authentication |  | https://www.figma.com/community/file/1192805634664589879/dashboard-app-ui-kit-21-screens-total
https://www.figma.com/design/a9iS3yn7uMp37csL3JpAte/Mint-Finance---Mobile-app--Community-?node-id=0-1&p=f&t=2bmeOVRUzgdf1RFO-0 |  | https://ui8.net/fluttertop-uiux/products/love-affection-dating-admin-panel-streamlining-your-dating-app-management
https://pngtree.com/freepng/login-mobile-ui-kit_5137563.html
https://www.figma.com/design/FMA6s1Jjr9vu4DygrPNlcv/Ice-Cream-Mobile-App---Dashboard--Community-?node-id=0-1&p=f&t=KXUi2Iser0Xo0UzM-0
https://www.figma.com/community/file/1291131035515876553/mobile-app-login-sign-in-template
https://www.figma.com/community/file/1261742596651461425/mobile-app-sign-in-sign-up-page

## Rules
For Developers | For Users
Updates to be provided to user only after every 6 - 8 months, so user can adjust/adapt to the updates | Do not share any personal details like mobile number,